## open questions
No | Question | Responsible | Deadline | Remarks | Solved (Y/N)
1 | How will contracts be registered? | L. István | 1.3.2019 | All the data of the old system must be entered into the new one | N
2 | How will the new ERP match SAMU? | G. Péter | 11.8.2019 | Design the interface | Y
3 | Games for team building? | N. Anna | 11.6.2019 | Arrange brainstorming session | N

## tasks assigned to others
No | Task | Responsible | Deadline | Priority | Remarks | Progress [%]
1 | Draft concept on dashboard | Adam | 12.8.2019 | 1 | Organize brain-storming | 70
2 | Hire new assistant | Lee | 11.5.2019 | 2 | Prepare profile | 25
3 | Prepare material for board | Beatrix | 19.6.2019 | 3 | Structure and outline | 100

## own tasks
No | Task | Deadline | Priority | Remarks | Progress [%]
1 | Check purchase contract | 1.5.2019 | 1 | Lawyers’ comments | 25
2 | Training new colleague | 11.5.2019 | 2 | Coordinate alignment list | 50
3 | Six-month report | 1.6.2019 | 3 | Customer satisfaction reports | 100